## Gantt Chart
Ronald Wastewater District Full Assumption Work Plan - September 25, 2019
Transition Plan Task |  | Project Manager | Project Support | Critical Task Prior to Assumption | RWD Coordination | Complete | Year 2019 | [11 empty] | Year 2020 | [11 empty] | Year 2021
[7 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
District Dissolution Process
| Draft Letter to the District Board of Commissioners setting forth the City's formal intential for assumption and assumption timeframe | City Manager | Assistant City Manager | x |  | x
| Draft Follow up Letter to the District Board of Commissioners Regarding updated assumption timeframe | City Manager | Assistant City Manager/City Attorney | x
| Prepare Joint Petition for District Dissolution (obtain District Board President signature on Joint Petition) | City Attorney | Assistant City Manager | x
| Draft and Present Final Assumption Ordinance to City Council if Supreme Court does not take Service Area Appeal Case | Assistant City Manager | City Attorney | x
| File petition of District Dissolution with King County Superior Court and receive Court Dissolution Approval | City Attorney | Assistant City Manager | x
| Notify King County Assessor of Assumption for property transfer | City Attorney | Assistant City Manager | x
| Notify King County Agencies of Assumption as per KC BRB order (County Council and Office of Performance Management and Budget) and notify WCIA | City Attorney | Assistant City Manager | x
Utility Advisory Board
| Prepare for Term-limited (three years) Wastewater Utility Advisory Board (WUAB) Creation and Management, including community with current District Board Members | Utility and Ops Manager | Public Works Director and Wastewater Manager | x | x
| Staff Term-limited Wastewater Utility Advisory Board | Utility and Ops Manager | Public Works Director and Wastewater Manager
Budget and Capital Improvement Plan
| Amend 2019-2020 Biennial Budget to incorporate District 2020 Operating and Capital Budget and fee table update | Budget and Tax Manager | ASD Director and Finance Manager | x | x
| Amend 2019-2020 Biennial Budget at the Mid-Bi to incorporate additional transition Costs | ASD Director | Budget & Tax Manager | x
Wastewater Planning, Engineering and Code Documents
| Create Wastewater Engineering Development Manual (EDM) Section | City Engineer | Development Review and Construction Manager, Operations Manager, Wastewater Manager | x
| Review adopted Wastewater Section of the SMC to see if any amendments are needed | City Attorney/Operations Manager | PW Director, Wastewater Maanger | x
| Cooridnate current work on Sewer Comprehensive Plan Update by District Engineer (CHS) | Operations Manager | Wastewater Manager, PW Director | x | x
| Review proposed Edmonds Wastewater Treatment Contract (expires May 2020) and transition contract to the City | Operations Manager, Wastewater Manager, PW Director | City Attorney | x | x
| Transition Paperwork for the King County Treatment Contract | City Attorney | Operations Manager, Wastewater Manager, PW Director
| Transition Paperwork for Olympic View Water-Sewer District | City Attorney | Operations Manager, Wastewater Manager, PW Director
| Planning for Sewer Comprehensive Plan Update | Operations Manager | Wastewater Manager, PW Director
| Wastewater Franchise for infrastructure in 145th Street and 205th Street under KC jurisdiction | City Engineer | City Attorney, Operations Manager |  | x
| Air Space Lease with WSDOT for I-5, SR-523 (145th Street) and SR-104 (205th Street) | City Engineer | City Attorney, Operations Manager |  | x
Permitting Issues
| Amend Developer Extension Process Update (forgoing District Board approval) | City Engineer | Operations Manager | x
| Connection Permit - District Board considering change | Operations Manager | City Engineer | x | x
| Transition Sound Transit Permit Processing and Inspection | City Engineer | LLE Project Manager, District Engineer | x | x
| Transition Construction Inspection on Capital and Development Projects | City Engineer | LLE Project Manager, District Engineer | x | x
| Update all Permit Documents to remove references to Ronald | Permit Services Manager | Finance Manager | x
| Sewer Permit Service Fee Cost Recovery Analysis | Operations Manager, Wastewater Manager | Development Review and Construction Manager, City Engineer, ASD Director, Finance Manager |  | x
| ROW permit process improvement (no separate permit needed) | City Engineer | Operations Manager
| Develop Process for Integrating Data Between the Financial Accounting/Utility Billing System and Trak-IT Permit System | IT Manager | ASD Director, Operations Manager, Finance Manager and IT Project Manager
Billing and Financial Issues
| Review Utility Tax in lieu of contract fee payment and franchise fee on bills and perform adjustments if needed | Finance Manager | ASD Director | x
| Coordinate with billing provider on updated billing layout and look and perform other billing transition tasks | Finance Manager | ASD Director | x
| Transfer Treasury Collection Funciton from King County to City | Finance Manager | ASD Director | x
| Coordinate transfer with Retail Lock Box for Utility billing | Finance Manager | ASD Director | x
| Coordinate with District Attorney and Transfer Utility Account Collections Process to City | Finance Manager | ASD Director, City Attorney | x | x
| Implement Over the Counter Credit Card Payment Processing for Utility Bills | Finance Manager | ASD Director, City Clerk
| Update wastewater permit fees to support cost recovery | Finance Manager | ASD Director, Operations Manager
| Creation of Capitalization Fund for all Wastewater major assets | Finance Manager | ASD Director, Operations Manager
| Grinder pump replacement charge assessment and recalculation | Finance Manager | ASD Director, Operations Manager
| Plan for transition of Real Property | Finance Manager | ASD Director | x | x
| Update Chart of Accounts and Accounting Processes to Accomodate Full Assumption | Finance Manager | ASD Director | x
| Develop Process for Integrating Data Between the Financial Accounting/Utility Billing System and Trak-IT Permit System | IT Manager | ASD Director, Operations Manager, Finance Manager and IT Project Manager
Purchasing and Contracts
| Engage Contract District Engineer (CHS; Scott Christiansen) for 2020 contract with City for general CIP support | City Engineer | Public Works Director, Operations Manager, Wastewater Manager | x | x
| Develop new contract for utility locates | Operations Manager | Wastewater Manager
| Develop contract for unit bid or Job Order Contracting repairs for utility lines (laterals and small lines) and equipment (generators and pumps) | Operations Manager | Wastewater Manager | x
Facilities
| Create direct fiber optic connection to Wastewater Building | IT Manager | Wastewater Manager, ASD Director and Fleet and Facilities Manager
| Assess and Fix Automatic Gate at Wastewater Building | Fleet and Facilities Manager | Wastewater Manager
| Assess and Rebuild ADA Ramp at Wastewater Building | Fleet and Facilities Manager | Wastewater Manager
| Update vehicle decals and Wastewater Building signage to remove District logos/markings | Fleet and Facilities Manager | Wastewater Manager
| Change out locks/security code on Wastewater Building and make other security fixes | Fleet and Facilities Manager | Wastewater Manager
| Conduct Facility Evaluation - develop long term facility plan | Fleet and Facilities Manager | Wastewater Manager
Operations Transition
| Finalize Operation and Maintenance Policy and Practices Documentation | PW Director | Operations Manager, Wastewater Manager | x | x
| Support District General Manager/District Attorney in the physical dissolution of the District (website shut down, documentation finalization, etc.) | Operations Manager | Finance Manager, Wastewater Manager, Fleet and Facilities Manager | x | x
| Assess Maintenance and Repair Policies for Side Sewers/Sewer Laterals | Operations Manager | Public Works Director, Wastewater Manager
| Assess Combined wastewater surface water staffing and work | Operations Manager | Public Works Director, Wastewater Manager
| Assess planning, contracting and engineering support for the longer term | Operations Manager | Public Works Director, City Engineer, Wastewater Manager
| Assess GIS records and district assets | Operations Manager | Public Works Director, Wastewater Manager
| Assess new or shared equipment needs and budget impacts | Operations Manager | Public Works Director, Wastewater Manager
| Assess moving additional staff to wastewater building | Operations Manager | Public Works Director, Wastewater Manager, Facilities Manager